## Balanced Scorecard
BALANCED SCORECARD: PROGRESS KIU ACCOUNTING
Objective Description | Digitalisasi dan integrasi menyeluruh modul operasional Kiu Accounting: Purchasing, Logistik, Sales, dan Keuangan.
Owner: Tim IT & Akuntansi | Measure lead: Kelengkapan Modul & Validasi Jurnal | Frequency: Mingguan | Overall Status: 95% ¦ Date: 10-Agu-26
Must Win | Key initiatives | Dasar Verifikasi / Sumber Data | Status
PURCHASING | 1. Purchase order komersil dan non komersil | System / User Acceptance Testing | 100%
| 2. Lpb penerimaan barang masuk | System / User Acceptance Testing | 100%
| 3. Bufferstock | System / User Acceptance Testing | 100%
| 4. Retur Pembelian | System / User Acceptance Testing | 100%
LOGISTIK | 1. Sistem pengaturan pengiriman barang | System / User Acceptance Testing | 100%
| 2. Activity Warehouse | System / User Acceptance Testing | 100%
| 3. Delivery Order | System / User Acceptance Testing | 100%
SALES | 1. Sales order | System / User Acceptance Testing | 100%
| 2. Digital Plafon | System / User Acceptance Testing | 100%
| 3. Penerbitan faktur | System / User Acceptance Testing | 100%
| 4. Retur Penjualan | System / User Acceptance Testing | 100%
| 5. Pengajuan OD | System / User Acceptance Testing | 100%
KEUANGAN | 1. Settingan kode akun dan Jurnal | System / User Acceptance Testing | 100%
| 2. Jurnal automatis | System / User Acceptance Testing | 100%
| 3. Neraca & Laba rugi | System / User Acceptance Testing | 100%
| 4. Jurnal umum | System / User Acceptance Testing | 100%
| 5. Buku besar | System / User Acceptance Testing | 100%
| 6. Kas masuk dan Kas keluar | System / User Acceptance Testing | 100%
| 7. Laporan | System / User Acceptance Testing | 30%
Total Capaian Kinerja Terverifikasi (Overall Score) |  |  | 95%
LEGEND: ¦ >= 100% (Tercapai) = Hijau ¦ <100% - 90% (On Progress) = Oranye ¦ <90% (Belum Start) = Merah
PENCAPAIAN TERVERIFIKASI | • Penyelesaian 100% modul Purchasing, Logistik, dan Sales. • Infrastruktur pendukung (Jurnal, Bufferstock, OD) telah teruji.
TANTANGAN & ISU LAPANGAN | • User Acceptance Testing (UAT) perlu dieksekusi secara utuh. • Modul Laporan Keuangan masih di tahap 30% dan membutuhkan atensi khusus.
RENCANA AKSI & MITIGASI RISIKO | • Eksekusi User Acceptance Testing (UAT) sebelum 29 Agustus 2026. • Fokus tim pengembang (Sprint) untuk menyelesaikan sisa modul Laporan.